## Slide 1
Challenges from the SARI Project
Sustainability Failures in Rural Telecenters
Amit Maniyar
(2007CS10154)
Ankit Narang
(2007CS10156)

## Slide 2: Objective
To examine the factors affecting sustainability of an ICT4D project in rural India, namely ‘Sustainable Access in Rural India (SARI) Project’
  To examine the reasons for sustainability failure of kiosks run by private entrepreneurs
  To understand how best to enhance the efficiency and effectiveness of such projects and to realize their long-term sustainability.

## Slide 3: The SARI Project
Started in November 2001
A collaborative venture of several organizations:
  Harvard, MIT, IIT Madras, McKinsey
Kiosks: Fees levied for various services
36 privately owned kiosks (Chirag kiosks)
42 kiosks operated by Dhan Foundation
By May 2005, 32 of the 36 Chirag kiosks had ceased to function
  Most of the Dhan kiosks were still operational

## Slide 4: The SARI Project (Contd.)
Project partners:
  Initial support: ICICI; Ray Stata
  Implementing partner: n-Logue Communication
  E-governance: local government & administration
  Other collaborations (e.g. Arvind Eye Hospital)
Institutional Framework:
  Laid out through the executive order of TN Govt.
  E-governance services: Madurai district collector
Business Model:
  A wide gamut of services
  User fees for services
  Voice services included (Never implemented)

## Slide 5: Research Methods
Priamary variable: duration fro which each telekiosk was “active”
Percentage of active Chirag kiosks in Melur, relative to those Percentage of active Dhan kiosks in Melur, relative to those
opened during that month opened by that month

## Slide 6: Possible Factors determining “Kiosk Life”
institutional, operational, and technical support provided by n-Logue
Initial functioning time
Different owner and operator
Villager’s liking of the facility
Owner’s opinion:
  No voice telephony
  Poor support from n-Logue
  Lack of financial returns
  Bad Internet Connectivity

## Slide 7: Significant factors
Lack of support from n-Logue
Different owner and operator
  Better coordination for service delivery
Prior computer training of the owner/operator
Lack of support from elected representatives
  Disinterest of politicians
  Transfers of administrators
Lack of adequate technical support
  High technolog maintenance costs
Failure of institutional linkages
  No incentive for the institutions
Lack of new content

## Slide 8: Differential Performance of Dhan and Chirag Kiosks
Dhan kiosks supported financially by Dhan Foundation
  No external financial support for Chirag kiosks
Assured operator wages in Dhan kiosks
Institutional support for developing new content
Subsidies for technological and operational expenses in Dhan kiosks, whereas no such option for private kiosks owners

## Slide 9: Critical Failure factors (1999)
Heeks and Bhatnagar factors:
  information, technical, people, management, process, culture, structure, strategy, politics, environment
    Lack of institutional support: Management, cultural, and structural factors
    Lack of technical support: Technical factor
    Lack of institutional partnerships: Management, process, and strategic factors
    Lack of new and relevant content: Information factors

## Slide 10: Critical Analysis
Strengths:
  A comprehensive study taking multiple factors into account
  Inclusion of qualitative & quantitative factors
  Concrete statistical calculations to arrive at conclusions
  Explaining failure factors in agreement with prior works on failure models

## Slide 11: Critical Analysis
Weaknesses:
  Firstly, a long and repetitive paper
  User feedback is missing
  No latent factors analysed

## Slide 12: Community Internet Access in Rural Areas: Solving the Economic Sustainability Puzzle

## Slide 13: ICTs for rural areas
  Conventional assumption:
    Need for subsidies
    Financial loss inevitable
  Sustainability requirements:
    Economic viability:
      Costs
      Capacity
      Revenue
      Networks
      Business models
      Policy
  Shared resources: Telecentres/Telekiosks

## Slide 14: Keeping Costs Low
  Capital cost reduction
    New cheaper hardware
    Wireless Network
  Recurrent cost reduction
    Telephone & Internet access technologies separating voice & data (e.g. corDECT)
    Power costs:
      Energy efficient devices (e.g. Pengachu)
      Alternative power sources (e.g. PV)

## Slide 15: Generating Revenue
Fee-for-services (e.g. e-commerce, education, entertainment)
Remote Services/back office activities
Aggregation of services & users

## Slide 16: Benefits of Scope & Scale
Value of internet grows with the square of number of users (Metcalfe effect)
Aggregation of rural networks
Context-appropriate business models

## Slide 18: Benefits of Scope & Scale
Creation of Rural Service Providers (RSP)
  Model similar to cable operators
  Flat cost structure
  Understanding of local market
Adding Telecenters to existing businesses
  E.g. off-hour use of labs to generate revenue
Adding businesses to Telecenters
  E.g. Computer repair, web design etc.

## Slide 19: Policies to support rural access
Increasing competition between providers
Removing regulatory barriers:
  Universal service & access requirement
  Cash Deposit requirement
  Wireless spectrum allocation
Incentives to support universal access
  E.g. In Bolivia no fee licenses were offered in exchange for commitment to rural service & education

## Slide 20: Policies to support rural access
Substituting dial-up connection
Use of VOIP to promote competition
Different metric for spectrum allocation

## Slide 21: Building Local Capacity
Basic management & accounting skills required
Outreach efforts by individuals, non-profits & public organizations needed
Red Científica Peruana offers training sessions for telecenter operators on weekly basis

## Slide 22: Critical Analysis
Strengths
  RSP model to make community internet access economically sustainable
  Remote services as source of revenue
  Generating employment/businesses by use of telecenters
  Aggregation of networks & thus exploiting economies of scale

## Slide 23: Critical Analysis
Weaknesses
  Elocution of the obvious
  Lack of concrete solutions
  Lack of supporting evidences